## Sheet1
Area | Task | Time in hours
Back End | Data Analysis | 27
| Data Modeling | 18
| Staging | 27
| Cube Building | 27
| Report MDX | 160
| Testing | 44
| Production Automation | 27
Front End | Prototyping | 27
| Layout design | 18
| Reports design | 66
| Interaction Implementation | 30
| Testing | 44
Project Management and QC | Business analysis and Task distribution with monitoring | 36
| Environment Setup | 18
| QC Overall | 44
| Deployment | 18
| Total | 631